SMS STEM PARTNERSHIP DRAFT WORK PLAN

July 2013-June 2014

Vision Statement

The South Metro-Salem STEM Partnership catalyzes Oregon students to achieve STEM degrees and certificates, and reach Oregon’s education goals by increasing the access, excitement and engagement of students in STEM courses and experiential learning.

Mission statement

The South Metro-Salem STEM partnership will collectively optimize PK-20 STEM education by utilizing a full spectrum of public and private resources and model instructional practices to develop a career-ready, diverse, and adaptable workforce that enhances the regional economy and community.

Goals and Expected Outcomes:

By 2025, the South Metro-Salem STEM Partnership will increase science and math achievement among students in partner districts and targeted schools.   The Partners will work to identify common assessments, consistent with standards that measure the skills necessary for post-secondary success and give feedback to students, families, teachers and administrators on what kids can demonstrate and what skills and knowledge they still need to gain.

Proposed measures include these options:

- By 2025, increase the percentage of the region’s 4th, 8th, and 12th graders that are “proficient” and “advanced” as measured by the NAEP.

- By 2025, increase the number of STEM college graduates that matriculate from partner schools.

- Increase STEM participation, persistence, and achievement based on ethnic/cultural and/or socioeconomic background, limited English language proficiency, gender, or disability.

- Improve Oregon business and industry access to an Oregon-educated STEM talent pool that is highly skilled, motivated and globally competitive.

Strategies:

- Create a learning community of teachers and community partners to share effective instructional practices (teacher coach/guided practice) and integrate science and engineering work samples into common core standards, with contextualized, experience-based teaching and learning methods.

- Build a “STEM Network” of mentors, programs and events that inspire students and sponsors to highlight the value of STEM activities (ISEF, FIRST, ORTOP, SeaPERCH, MATE, Physics Bowl, Math Olympiad, Skills USA, museums, aquariums, libraries, etc.), connect STEM activities to the classroom, and utilize the region’s rich industry and community resources.

- Expand collaborations between schools, colleges and universities to accelerate students through dual credits, advanced placement, and incentives to attract students into STEM degree paths.

|  | Build Engagement and Resources | Sept 2012- June 2013 | July 2013 – June 2014 |
| --- | --- | --- | --- |
| PARTNERS | Learning Tour: STEM Bus Tour with Superintendents | December 14, 2012- Done |  |
|  | Partnership Launch: Mentor Graphics | January 11, 2013- Done |  |
|  | Learning Tour and Showcase: Evergreen |  | Jan 2014 with STEM Network Director |
|  | Submit grant proposals for state funds: professional development and STEM Hub | 21st Century grants to McMinnville, North Clackamas, Oregon City, Salem-Keizer, Woodburn | Oct 2013: PD Jan 2014: STEM Hub Others: CTE, etc |
|  | Submit grant proposals to private funders |  | -MESA-Salem-Keizer -OCF and Murdock |
|  | Strategy 1: STEM Network of industry and community resources for schools |
| INDUSTRY AND COMMUNITY | Establish electronic matching system to connect industry and community resources to schools and teachers | - Explore existing tools such as CIS Connect and Intel Engage | -License CIS Connection with three workforce regional partners |
|  | 2.2 Develop business and community capacity to populate STEM Network and understand how to offer meaningful experiential learning | - Host STEM Learning Tour for superintendents | -Hire STEM Network Director – Aug -Populate CIS Connection with volunteer opportunities |
|  | 2.3 Develop teacher capacity to use STEM Network |  | -Populate CIS Connection with teacher and student needs |
|  | 2.4 Align menu of STEM Network volunteer experiences with CCSS and NGSS to support learning outcomes. |  | -Consultant contract to work crosswalk volunteer experiences with CCSS and NGSS |
|  | Strategy 2: Teacher Professional Development |
| TEACHERS | 1.1 Establish professional learning community to share effective practices and STEM curriculum among partners, and determine professional development model | -Develop professional development framework and plan for 2013-2014 academic year -Appoint three teacher reps for each district to be first learning community cohort | - Convene learning community- September -Identify effective practices/ map assets- Oct- Jan -Identify and develop STEM coaches -Conduct summer PS; ongoing support plan |
|  | 1.2 Assist teachers to effectively utilize community and business volunteers to support common core standards (CCSS) and next generation science standards (NGSS) |  | -Incorporate STEM Network into learning community process -Utilize STEM Network Director to build support and use of the tool |
|  | Strategy 3: Accelerated STEM college credit through expanded school, college, university collaborations |
| STUDENTS | 3.1 Develop articulated programs between partner schools, colleges and universities, and increase college-going incentives | -Implement Oregon Tech OWLS program and incentives- Done - Build cadre of faculty and students to engage in classrooms, with teachers and parents | -Add dual credit options with all 13 school districts -Collect baseline data |
|  | 3.2 Increase % of partner high school students getting accelerated credits | - Inventory current options for high school transitions and dual HS-college credit | -Market available college courses -Address barriers related to teacher “qualification” -Explore credit for proficiency options |